## Slide 1
MD 2026-2030 SHSP Development

## Slide 2: Who is Crash Core?
Crash Center for Research and Education
Established in 2018
Engineers, Data Scientists, Software Developers

## Slide 3: Mission
To conduct the research necessary to educate its audience beyond the commonly known, then communicate the message that allows a deeper insight to fully appreciate the science of safety

## Slide 4: MHSO Project Examples
Development of SHSP 2021-2025
Evaluation of Automated Enforcement
MD MOTORS Coordination
Crash Science/EMS Training
MD Crash Forecasting (POTIF)

## Slide 5: SHSP 2026-2030 Development Project Team
Janet Bahouth
Project Director
Becca Drayer
Program Manager
Rebecca Spicer
Data Scientist
Bekah Thomas
Workshop Moderator
Cara Lustik
Writer

## Slide 6: Review of Relevant Work/Literature
Current and previous MD SHSPs
Safe System Approach literature
Other state SHSPs
GHSA’s Guidance for Developing Highway Safety Plans
Other
Projected Timeline: October 2024

## Slide 7: Create 2026-2030 SHSP Development Plan and Hold Kickoff Meeting
Hold Kickoff Meeting to present plan to Executive Committee for approval to include:
  Outline of tasks
  Timeline
  Milestones
  Budget and communication controls
  Stakeholder outreach process
  Projected Timeline: October 2024-November 2024

## Slide 8: Stakeholder Engagement
One on One Interviews with key stakeholders (TBD by MHSO)
  Draw stakeholders’ insight and feedback on the state of highway safety in Maryland including current and future safety priorities
Online Survey to larger stakeholder group (TBD by MHSO)
  SHSP emphasis area goals
  Proposed action steps
  Identification of emerging issues
  Ideas for evaluating SHSP progress
  Thoughts on how to maintain the SHSP’s relevance throughout the 2026-2030 term
Projected Timeline: December 2024-February 2025

## Slide 9: Obtain EATs’ SHSP Feedback and Contributions
Interviews with EAT Chairs
EAT Team Workshops (One full day in person one ½ day virtual)
  SHSP emphasis area goals
  Proposed action steps
  Identification of emerging issues
  Ideas for evaluating SHSP progress
Projected Timeline: December 2024-March 2025

## Slide 10: Develop Draft of 2026-2030 MD SHSP
Compile feedback from interviews, surveys, and workshops
Work with writer and graphic designer to develop draft for MHSO review and feedback
Projected Timeline: April 2025-June 2025

## Slide 11: Finalize Document
Incorporate feedback and edits from draft review
Submit to Executive Committee and MHSO for final approval
Projected Timeline: June 2025-July 2025

## Slide 12
2024
117 days
27 days
Today
56 days
60 days
117 days
2025
30 days
Oct 1 - Oct 31
29 days
Nov 1 - Nov 30
Stakeholder Engagement
EA Feedback
Develop Draft
Finalize Document
Literature Review
SHSP Development Plan & Kickoff
Oct
Nov
Dec
2025
Feb
Stakeholder Interviews and Survey
EA Chair Interviews
Workshops
Mar
Apr
May
Jun
Develop and Submit Draft
Develop and Submit Final
Jul
Review Literature
Develop Plan
SHSP Development Timeline

## Slide 13
Questions?
Becca Drayer
bdrayer@crashcoremd.org

## Slide 14: Develop and Deliver “What is the SHSP?” Presentation (October 2024-December 2024)